## Instructions
Project schedule for simple projects
This workbook is a schedule template for simple (small) projects. It can be used to provide a starting point for developing a schedule to manage a project.
The template has three elements to it:
1) List of milestones. These show the overall progress of the project and are used in reporting to the Business Owner (Project Sponsor) and other stakeholders. The dates indicate when the respective milestone will or has been achieved, and they are read from the respective lines in the actual schedule.
2) Activities grouped by project phase and most common outputs from projects. The Project Manager / Project Coordinator should update this section continuously to reflect the true state of and plans for the project.
3) Post-project operations. These are common activities which take place after the project has closed. Some of them can start while the project is implemented. They should be handed over to and performed by the respective stakeholders.
Two lists at the bottom of the schedule worksheet are used in formulas related to durations and costs and if any modifications are made, the respective name ranges and formulas should be updated, where needed.
HOW TO USE THE TEMPLATE?
Data in cells with white background can be freely changed to suit the project. Data with pale grey background is calculated based on inputs and re intended to remain as are.
Especially in the Implement Phase section, the Project Manager can freely add and remove stages and individual activities. Please note, however, that the approach recommended in the schedule intends to prompt for planning of readiness and handover / adoption activities and should be included in the schedule in a form that best suits the project.
Resource names can be changed, as required. A good practice is to refer to roles rather than individual names but this is left at the Project Manager's discression. If resource names are changed or new ones added, the relevant staff cost should be reflected in the respective section below the schedule.
FIELDS USED FOR SCHEDULING
The following fields are used in the schedule. Additional fields can be freely added, if needed.
Completed during the project planning, updated throughout the project
* Activity - The name of each individual activity, summary-level activity or grouping. Each activity should start with a verb, followed by an object.
* Work (d) - The work effort estimated for each activity. Expressed in workdays or part days (e.g. '3' for 3 days, '0.5' for half a days worth of effort). Please remember to sum up or multiply the effort by the number of staff engaged in the activity (e.g. three staff doing two days each = 6).
* Start - The date the task is planned to start or did start.
* Finish - The date the task is planned to be finished or did finish.
* Duration (d) - Calculated automatically. The number of workdays (in calendar) spent on an activity.
* Resources - The staff, stakeholders and suppliers engaged in working on an activity. The names listed here need to be included also in the 'Costs' section at the bottom of the worksheet with their respective salary or other cost level. Staff salaries can be found in the Enterprise Agreement (link below). The summary % on top of the worksheet indicates the overall FTE load (Work (d) compared to duration).
ACU Enterprise Agreement
* Cost (d) - Calculated automatically. The cost of work for an activity. If the project is funded from operational funds (opex), the total amount is what the respective financial delegate is looking to spend from their funds. The cost is calculated by using the 'Costs' list at the bottom of the worksheet. The resource name on an activity is looked up from the list and the respective daily cost is returned back to the formula. If an activity has procurement costs, they can be added to the respective cell.
Updated throughout the project (control the project)
* Done (d) - The number of workdays spent so far or in total on an activity.
* Done % - Calculated automatically. The ratio of work done compared to the planned work (i.e. 'Done (d)' divided by 'Work (d)', expressed as %). If the work has taken less effort to complete, the value should be overridden and marked as 100%. The total % value in the 'Project delivery overall' row is the "% complete" and can be used in reports.
* Expense - Automatically calculated. Multiplies the daily cost by the days spent (i.e. Cost (d) * Done (d)). Any procurement costs should be added seperately.
PROJECT DELIVERY OVERALL BANNER
This banner summarises the data in the schedule. If you amend rows into the schedule, please ensure the formulas in this section cover the plan, implement and close phases of the project. 'Workload' indicates the total FTE load but does not distinguish between roles. The 'Cost estimate' is the total cost that the Business Owner needs to be prepared to allow the project to use.
The fields 'Done (d)', '% complete', and 'Actual cost' refer to the realised effort and cost as entered by the Project Manager. The "traffic lights" below them indicate the health of the parametres compared to the planned values. Green (text "OK") = actuals below the planned values, amber (text "Monitor") = max 10% overrun, red (text "Review!") = overrun at least 10% and the project plans and delivery should be reviewed with the Business Owner.
Please note that this template does not facilitate baselines! Baselines refer to the approved budget and timeline, and facilitate comparisons of the actual progress against those. If this needs to be reported in the project, a simple way to assist this is to add the respective information about approved budget and timeline near the 'Project delivery overall' section and write the respective narrative in the status reporting.

## Schedule
|  |  | <PROJECT NAME> |  | 2019-03-20 | (last updated)
|  |  | Project schedule |  | <Name> | (updated by)
| Work (d) | Start | Finish | Duration (d) | Workload | Cost estimate | Done (d) | % complete | Actual cost
PROJECT DELIVERY OVERALL | 186.5 days | 2019-03-25 | 2019-07-06 | 103 | 129.5% | 96120 | 0 days | 0% | 0
[7 empty] | OK |  | OK
PLANNING | [6 empty] | PROJECT CONTROL
ACTIVITY | Work (d) | Start | Finish | Duration (d) | Resources | Cost (d) | Done (d) | Done % | Expense
MILESTONES
Business Case or Proposal approved |  |  | 2019-03-15
Project planning approved |  |  | 2019-04-10 |  |  |  |  | 0% | 0
Project outputs completed |  |  | 2019-06-07 |  |  |  |  | 0% | 0
Operational readiness developed |  |  | 2019-06-05 |  |  |  |  | 0% | 0
Commence operational use |  |  | 2019-06-12 |  |  |  |  | 0% | 0
First benefits measurement |  |  | 2019-07-01 |  |  |  |  | 0% | 0
Project closed |  |  | 2019-07-06 |  |  |  |  | 0% | 0
PLAN PHASE
Confirm business requirements | 2 | 2019-03-25 | 2019-03-29 | 5 | Business Owner, Project Manager | 1500 |  | 0% | 0
Develop plans
Confirm budget | 0.5 | 2019-03-28 | 2019-03-29 | 2 | Project Manager | 330 |  | 0% | 0
Develop schedule | 0.5 | 2019-03-28 | 2019-03-29 | 2 | Project Manager | 330 |  | 0% | 0
Identify risks (risk workshop) | 2 | 2019-04-01 | 2019-04-01 | 1 | Business Owner, Project Manager, delivery team | 1250 |  | 0% | 0
Develop PID | 2 | 2019-04-02 | 2019-04-05 | 4 | Project Manager | 1320 |  | 0% | 0
Review PID | 0.5 | 2019-04-08 | 2019-04-09 | 2 | Business Owner | 420 |  | 0% | 0
Approve PID | 0 | 2019-04-10 | 2019-04-10 | 1 | Business Owner | 0 |  | 0% | 0
IMPLEMENT PHASE
Stage 1 - First output from the project
<The activities required to develop the output> | 10 | 2019-04-11 | 2019-04-26 | 9 | Delivery team | 5000 |  | 0% | 0
<The activities required to develop the output> | 4 | 2019-04-27 | 2019-04-30 | 2 | Delivery team | 2000 |  | 0% | 0
<The activities required to develop the output> | 9 | 2019-05-01 | 2019-05-10 | 8 | Delivery team | 4500 |  | 0% | 0
<The activities required to implement the output> | 1 | 2019-05-11 | 2019-05-13 | 1 | Delivery team | 500 |  | 0% | 0
<The activities required to implement the output> | 21 | 2019-05-14 | 2019-05-22 | 7 | Delivery team | 10500 |  | 0% | 0
<The activities required to implement the output> | 4.5 | 2019-05-23 | 2019-05-24 | 2 | Delivery team | 2250 |  | 0% | 0
First output complete |  |  | 2019-05-24
Stage 2 - Second output from the project
<The activities required to develop the output> | 8 | 2019-04-25 | 2019-05-10 | 11 | Delivery team | 4000 |  | 0% | 0
<The activities required to develop the output> | 2 | 2019-05-11 | 2019-05-14 | 2 | Delivery team | 1000 |  | 0% | 0
<The activities required to develop the output> | 5 | 2019-05-15 | 2019-05-24 | 8 | Delivery team | 2500 |  | 0% | 0
<The activities required to implement the output> | 3 | 2019-05-25 | 2019-05-27 | 1 | Delivery team | 1500 |  | 0% | 0
<The activities required to implement the output> | 5 | 2019-05-28 | 2019-06-05 | 7 | Delivery team | 2500 |  | 0% | 0
<The activities required to implement the output> | 1 | 2019-06-06 | 2019-06-07 | 2 | Delivery team | 500 |  | 0% | 0
Second output complete |  |  | 2019-06-07
Operational readiness
<Potential process adjustment activities> | 30 | 2019-05-01 | 2019-05-15 | 11 | Delivery team | 15000 |  | 0% | 0
<Potential process adjustment activities> | 8 | 2019-05-16 | 2019-05-20 | 3 | Delivery team | 4000 |  | 0% | 0
<Potential process adjustment activities> | 25 | 2019-05-21 | 2019-05-31 | 9 | Delivery team | 12500 |  | 0% | 0
<Potential team internal comms / training> | 2 | 2019-05-01 | 2019-05-10 | 8 | Delivery team | 1000 |  | 0% | 0
<Potential team internal comms / training> | 18 | 2019-05-11 | 2019-05-28 | 12 | Delivery team | 9000 |  | 0% | 0
<Potential team internal comms / training> | 10 | 2019-05-29 | 2019-06-05 | 6 | Delivery team | 5000 |  | 0% | 0
Operational readiness complete |  |  | 2019-06-05
Handover to operational use
<Final preparations before operations> | 1 | 2019-06-06 | 2019-06-06 | 1 | Delivery team | 500 |  | 0% | 0
<Final preparations before operations> | 0.5 | 2019-06-07 | 2019-06-09 | 1 | Delivery team | 250 |  | 0% | 0
<Final preparations before operations> | 2 | 2019-06-10 | 2019-06-11 | 1 | Delivery team | 1000 |  | 0% | 0
<Commence operational use> | 1 | 2019-06-12 | 2019-06-12 | 1 | Business Owner | 840 |  | 0% | 0
<Commence operational support services> | 1 | 2019-06-12 | 2019-06-12 | 1 | Support services | 500 |  | 0% | 0
Handover complete, commence operational use |  | 2019-06-12 | 2019-06-12
Approve / sign off implementation | 0 | 2019-06-21 | 2019-06-21 | 1 | Business Owner | 0 |  | 0% | 0
CLOSE PHASE
Notify stakeholders of implementation | 0.5 | 2019-06-24 | 2019-06-24 | 1 | Project Manager | 330 |  | 0% | 0
Review project
Review project against plans | 0.5 | 2019-06-25 | 2019-06-25 | 1 | Project Manager | 330 |  | 0% | 0
Run lessons learned workshop | 2.5 | 2019-06-27 | 2019-06-27 | 1 | Business Owner, Project Manager, delivery team | 1570 |  | 0% | 0
Identify follow-on recommendations | 1 | 2019-06-28 | 2019-07-02 | 3 | Project Manager | 660 |  | 0% | 0
Develop PIR | 2 | 2019-06-28 | 2019-07-03 | 4 | Project Manager | 1320 |  | 0% | 0
Review PIR | 0.5 | 2019-07-04 | 2019-07-05 | 2 | Business Owner | 420 |  | 0% | 0
Approve PIR | 0 | 2019-07-06 | 2019-07-06 | 0 | Business Owner | 0 |  | 0% | 0
Project closed |  | 2019-07-06 | 2019-07-06
POST-PROJECT OPERATIONS | 12 days | 2019-07-01 | 2019-09-30 | 91 days | 8.824% | 9990 | 0 days | 0% | 0
Measure benefits, sustain outcomes | 1.5 | 2019-07-01 | 2019-09-30 | 66 | Business Owner | 1260 |  | 0% | 0
Reinforce business change | 10 | 2019-07-01 | 2019-09-30 | 66 | Business Owner | 8400 |  | 0% | 0
Close project financials | 0.5 | 2019-09-25 | 2019-09-30 | 4 | Management Accountant | 330 |  | 0% | 0
COSTS
Delivery team |  |  |  |  | HEW7.3 + on-costs 27.5% | 500
Project Manager |  |  |  |  | HEW9.3 + on-costs 27.5% | 660
Business Owner |  |  |  |  | Negotiated salary $150K | 840
Support services |  |  |  |  | HEW7.3 + on-costs 27.5% | 500
Management Accountant |  |  |  |  | HEW9.3 + on-costs 27.5% | 660
Business Owner, Project Manager |  |  |  |  | Average of above | 750
Business Owner, Project Manager, delivery team |  |  |  |  | Biased average of above | 625
PUBLIC HOLIDAYS
Good Friday |  |  | 2019-04-19
Easter Monday |  |  | 2019-04-22
Anzac day |  |  | 2019-04-25
Queen's birthday |  |  | 2019-06-10
Labour day |  |  | 2019-10-07
Christmas holiday |  |  | 2019-12-23
Christmas holiday |  |  | 2019-12-24
Christmas holiday |  |  | 2019-12-25
Christmas holiday |  |  | 2019-12-26
Christmas holiday |  |  | 2019-12-27
New Year |  |  | 2019-12-30
New Year |  |  | 2019-12-31
New Year |  |  | 2020-01-01
New Year |  |  | 2020-01-02
New Year |  |  | 2020-01-03
New Year |  |  | 2020-01-04
Formulas:
Start = [Finish, row above]+1
Start = [Start, row above]
Finish = MAX(D32:[Finish, row above])
Finish = [Finish, row above]
Duration (d) = DAYS([Finish],[Start])
Duration (d) = NETWORKDAYS([Start],[Finish],Holidays)