## Overview and Instructions
BUSINESS CHANGE PLAN
GUIDING PRINCIPLES
This Business Change Plan covers the activities that will be undertaken to move towards the desired future state in a business change. It articulates the objective for each change within a project and acknowledges that successful change is achieved through all staff working together towards this common goal in their respective roles (see below).
Example changes are provided for guidance and are from a project with multiple stages. Use your own project objectives when you fill in the template, e.g. implementing a new system, intoducing a new process or organisational framework or strategy. Then fill in your own changes.
The plan gives an overview of all neccessary change activities, and the high-level steps required. Some steps will be further detailed in other documents as referenced in the relevant step (e.g referring to various plan documents, white papers or recommendations).
The plan is a living document, maintained throughout the project with any new changes identified or adjustments to activities planned.
ROLES
Business Change Manager: A role which is responsible for the planning and delivery of the business change acitivities. This role can also be called Business Change Specialist. They work under the direction of the Business Owner (Project Sponsor) and in close collaboration with the Project Manager. Sometimes the Business Owner or Project Manager may assume the tasks of this role, especially in small or medium-sized projects.
Change Leads are responsible for introducing a change initiative to the relevant stakeholders and giving context on why the change is needed. Change Leads also work to establish feedback mechanisms and facilitate productive communication throughout the change.
Change Champions are key influencing roles which work with stakeholders to promote the benefits of the change. They help people to find their place as contributors to the initiatives and to become Change Enablers.
Change Enablers are all staff who adjust to the change and make active contributions to ensure its success and to help overcome challenges that may arise.
CHANGE MODEL
The ADKAR model of change is considered for changes which have a significant 'people' element. ADKAR represents the five outcomes that support individuals and teams to successfully adapt to and enable change. These are recorded in the 'Steps required' field of the plan.
Awareness - Understanding the business reasons for change. Awareness is a goal/outcome of early communications related to an organizational change.
Desire - Willingness to engage and participate in the change. Desire is a goal/outcome of sponsorship and resistance management.
Knowledge - Information about how to change. Knowledge is a goal/outcome of training and coaching.
@bility - Ability to realise or implement the change at the required performance level. Ability is a goal/outcome of additional coaching, practice and time.
Reinforcement - Ensuring that the change sticks. Reinforcement is a goal/outcome of adoption measurement, corrective actions and recognition of successful change.
FIELDS USED
Fields with white background are used to enter data. Fields with grey background are linked to other fields in the workbook and should be edited only if necessary.
Change Identification - Completed in the Initiate Phase in conjunction of the Business Case
ID - A unique identification of each change activity.
DESCRIPTION OF CHANGE - Describe the initiative
OBJECTIVE - What will happen because you're making the change
TYPE - Change category (People, Process, System, or Structure).
TARGET DELIVERY MONTH - Copied from the 'Change Planning' sheet. The month when the change activity is expected to be complete, including any reinforcement.
IMPACT SUMMARY - What will be affected by the change?
BENEFITS - What we are hoping the change will improve
RISKS - Note any risks that needed ot be avoided/managed
PRIORITY - Update as needed
Change Planning - Completed in the Planning Phase in conjunction of the Project Initiation Document (PID)
ID - Copied from the 'Change Identification' sheet. A unique identification of each change activity.
DESCRIPTION OF CHANGE - Copied from the 'Change Identification' sheet. Describe the initiative
RELATED CHANGE - List any other relevant changes which are related to the initiative
WHAT STAYS THE SAME - Stating this helps stakeholders be clear on the scope of the change
STEPS REQUIRED - List all the separate activities required, or refer to documents which contain this detail. Plan to communicate the impacts and the benefits of each change to stakeholders who are affected or involved. Refer to the ADKAR model to identify the outcome types expected.
START DATE - Update as needed
TARGET DELIVERY DATE - Update as needed
PRIORITY - Copied from the 'Change Identification' sheet. Change the value here, if needed, as the project needs evolve.
CHANGE LEAD/S - See Change roles above
CHANGE CHAMPION/S - See Change roles above
CURRENT STATUS - Select from: Planned, In progress, Complete.

## Change Identification
BUSINESS CHANGE IDENTIFICATION
<Project name>
This worksheet identifies all the activities to be undertaken to move towards the desired future state in a business change and outlines the objectives, benefits and risks. The implementation of each activity is then detailed in the Business Change Plan in the next worksheet.
| Business Change Manager | <Name> |  |  | Date | 2019-10-14 | Version | 1
ID | DESCRIPTION OF CHANGE | OBJECTIVE | TYPE | TARGET DELIVERY MONTH | IMPACT SUMMARY | BENEFITS | RISKS | PRIORITY
1 | Establish a Service Central office space. | Create Service Central at Melbourne campus. | Structure | 2018-10-22 | Resources and appropriate office space need to be allocated, and may require reallocation of other staff to other locations. | Physical contact centre will be centralised at Melbourne campus but service the whole university. Team cohesion and access to one another are supported by being located in one place. | A lack of suitable colocation could impact on team environment and knowledge transfer. | High
2 | HR service providers adopt Service Central and new ways of service management. | Competent and consistent use of ServiceNow as per the Service Central model. | People | 2018-12-21 | Staff time and effort will be required to attend training and to get comfortable with using the changed system and new ways of working. | An enhanced service experience and greater functionality for HR. A single and consistent approach to service management via ServiceNow across the Portfolio, cost and efficiency savings, long-term ability to triage non-HR requests to the correct area. The transition is also an opportunity to build upon the good service practices developed by HR and define and embed an excellent service culture across the Portfolio through use of supporting service protocols. | Service providers resist learning new ways to use ServiceNow and do not give constructive feedback which could help ACU best implement new processes and configurations for ServiceNow. Directorate service providers lose confidence in Service Central's effectiveness if too many Level 1 queries are referred to the Directorate, rather than being resolved by Service Central staff. | Medium
3 | Design the Service Central online portal. | Design a user-friendly, intuitive, attractive and functional portal for staff that will facilitate access to Corporate Services. | System | 2018-10-31 | Staff time and effort will be needed to use the prototype and give feedback. | Ensuring portal design meets user needs and is most effective and efficient to use. | Not enough staff across diverse range of areas give their honest feedback, leading to a limited view of the portal and its functionality. Limited buy-in to the resulting portal because business areas do not feel that they were consulted, and that the design is user-centric. | Medium
4 | Design an approach to UAT and user feedback for pre go-live Service Central releases. | Design the Service Central online portal. | Process | 2018-10-15 | Staff time and effort required to input into UAT design and to provide feedback on prototypes. | Ensuring that the portal design meets user needs and the interface is easy and effective to use for both service recipients and providers across ACU. | Lack of user input to design the portal. Low usage of the Service Central portal if the design is not user-friendly and easy to use. | Medium
Note on E7: Copied from the 'Change Planning' worksheet.

## Change Planning
BUSINESS CHANGE PLAN
<Project name>
This Business Change Plan outlines the details and dependencies of each activity within a business change, as identified in the previous sheet. The plan acknowledges that successful change is achieved through all staff working together towards this common goal in their respective roles (see Overview sheet for a definition of each role). The ADKAR model of change is considered for changes which have a significant 'people' element. Awareness, Desire, Knowledge, @bility, Reinforcement (see Overview sheet for further description).
| Business Change Manager | <Name> |  |  |  |  | Date | 2019-10-14 | Version | 1
ID | DESCRIPTION OF CHANGE | RELATED CHANGE | WHAT STAYS THE SAME | STEPS REQUIRED | START DATE | TARGET DELIVERY DATE | PRIORITY | CHANGE LEAD/S | CHANGE CHAMPION/S | CURRENT STATUS
1 | Establish a Service Central office space. | Recruit, appoint and onboard Service Central positions. |  | Determine location on Melbourne campus. Arrange office fitout. Arrange telephony set up. | 2018-07-02 | 2018-10-22 | High | Service Central Project Team | Service Central Steering Group | In Progress
2 | HR service providers adopt Service Central and new ways of service management. | HR's service management mechanisms and reporting processes (within ServiceNow) will change. Service recipients will have a new portal (Service Central) by which to access HR services and to track their HR service requests. | HR staff will retain access to input into, and view, ServiceNow. | A & D: Give guidance to Change Leads on how to successfully foster support for change amongst staff. @: The Change Leads assess change readiness (of HR service providers) and provide feedback on staff perceptions of readiness to Steering Group/Project Team before proposed go-live. A & D: Raise HR staff awareness of the rationale and process for transitioning (see Communications Plan). A & D: A demonstration of the Service Central prototype is given for HR staff (see Communications Plan) K: Share the Transition Plan with affected HR staff and invite feedback to refine it. (see Communications Plan). Change lead establishes feedback mechanisms. K & @: Train HR service providers in ServiceNow usage (refer to HR training plan). Disseminate support materials, set expectations about Service Central model reporting mechanisms. R: Acknowledge staff feedback contributions to the transition plan, report back and commend constructive suggestions and behaviours. A & D: Communicate how the transition and go-live of HR in the Service Central model will occur and the expected benefits. R: After go-live, recognise and celebrate changed ways of working and behaviours which support the new ways of working. | 2018-08-20 | 2018-12-21 | Medium | Service Central Project Team and staff, Directorate Leadership Team | Directorate Leadership Team, HR Standards and Reporting | Planned
3 | Design the Service Central online portal. | By May 2019, Corporate Services for staff will be accessed via the Service Central. | The existing IT Service Portal will remain the same, until IT are integrated into Service Central in 2019. | Design prototype with implementation partner (RXP). A & D: Socialise prototype with a wide range of selected service recipients and service providers to obtain feedback and make improvements before go-live, using established UAT and feedback mechanisms. A & @: Establish a reference group to assist with feedback on the build and functionality of the Service Central portal. | 2018-05-14 | 2018-10-31 | Medium | Service Central Project Team | Steering Group members and relevant Directorate/Portfolio representatives | In Progress
4 | Design an approach to UAT and user feedback for pre go-live Service Central releases. | Design the Service Central online portal. | A focus on improving the service user experience to achieve service excellence. | A & D: Seek input from IT to design a UAT and feedback approach, to incorporate lessons learned from IT Service Portal design and launch. | 2018-07-16 | 2018-10-15 | Medium | Service Central Project Team | Steering Group members and relevant Directorate/Portfolio representatives | In Progress
Note on A7: Copied from the 'Change Identification' worksheet.
Note on B7: Copied from the 'Change Identification' worksheet.
Note on I7: Change leads are responsible for introducing a change initiative to the relevant stakeholders and giving context on why the change is needed.
Note on J7: Change Champions are key influencing roles which work with stakeholders to promote the benefits of the change.