## Financial model
Business Case financial model workbook
This workbook supports the development of a simple financial model for Proposals for Business Change, and Business Cases.
Do the estimations on rows 23 to 44 by entering the respective data in green-coloured cells. The resulting financial model is on rows 48 to 69.
The relevant sections are copied from here into the Business Case.
HOW TO COMPLETE THIS?
1) Complete the Project Complexity Assessment. The results from it will be used as input to the financial model.
2) Enter your best case estimate for the project costs and financial benefits in the green cells below (rows 21-44). | [7 empty] | Salary levels (Jul 2019):
3) Enter the complexity assessment results in the green section below (row 21). | [6 empty] | Level | Annual cost
4) Copy the financial summary to your Proposal for Business Change (from row 48) or two sections to the Business Case (from row 59). | [6 empty] | Junior staff HEW 3 | 76108.56
5) For the Business Case, copy the green section (from row 21) to Appendix 1. | [6 empty] | Junior staff HEW 4 | 84571.84
[7 empty] | Junior staff HEW 5 | 94482.92
PLEASE NOTE | [6 empty] | Mid staff HEW 6 | 105031.54
Do the estimation by entering known data or best guesses in green cells. | [6 empty] | Mid staff HEW 7 | 116753.64
Notice that the first estimate is done for the initial Proposal when the benefits and costs can be estimated only as a magnitude ("ballpark"). The analysis done for the Business Case will refine this much further and help to produce figures with medium or high degree of confidence. | [6 empty] | Senior staff HEW 8 | 133135.37
A full work year assumes 231 workdays or 21 days * 11 months. | [6 empty] | Senior staff HEW 9 | 152868.63
[7 empty] | Senior staff HEW 10 | 177904.14
↓ Enter the input in the green cells in this section ↓ | [5 empty] | This section is also copied into the Business Case and PID, Appendix 1 | National Manager | 165100
[7 empty] | Associate Director | 203200
Achievability | 90% | Benefits |  | 90% | Delivery |  | Director | 254000
FINANCIAL BENEFITS | $ in 2020 | $ in 2021 | $ in 2022 | $ in 2023 | $ in 2024
Financial benefits / revenue (positive impact) $ | 250000
EXTERNAL COSTS (capex)
Professional services / consulting $
IT specialist staff cost | 100000
Permits / licensing (Initial / 1st year cost $) | [6 empty] | CONVERSION OF WORKDAYS TO COST
[7 empty] | 0 | 1 | 2 | 3 | 4
INTERNAL COSTS (opex) | [5 empty] | Level | Cost 2020 | Cost 2021 | Cost 2022 | Cost 2023 | Cost 2024
Senior stakeholders | [5 empty] | Director | 0 | 0 | 0 | 0 | 0
Project Manager / coordinator | 105 |  |  |  |  | Senior staff HEW 9 | 69485.7409 | 0 | 0 | 0 | 0
SME's | [5 empty] | Senior staff HEW 8 | 0 | 0 | 0 | 0 | 0
Other teams in ACU | [6 empty] | 0 | 0 | 0 | 0 | 0
Process / System Owner | [6 empty] | 0 | 0 | 0 | 0 | 0
Other resources - IT Sol architect, integration | [6 empty] | 0 | 0 | 0 | 0 | 0
Other resources (specify) | [6 empty] | 0 | 0 | 0 | 0 | 0
ON-GOING OPERATIONAL COSTS | [5 empty] | Level
Support / maintenance services $
Permits / licensing (annual cost, $) | 30000
Staff load (workdays /year) | [6 empty] | 0 | 0 | 0 | 0 | 0
Staff load (workdays /year) | [6 empty] | 0 | 0 | 0 | 0 | 0
↓ Copy the section below into the Proposal for Business Change ↓ |  |  | Copy area B53:E58
| Simple | Medium | Complex
Complexity |  |  | Complex
| Best case | Projected | Worst case
Financial benefits | 250000 | 237000 | 225000
| Best case | Projected | Worst case
Cost | 200000 | 220000 | 230000
↓ Copy the section below into the Business Case ↓ |  |  | Copy area B59:E69 |  |  | Copy area G59:H64
Copy to section 'Financial Model' |  |  |  |  | Copy to 'Executive Summary'
FINANCIAL BENEFITS | Best case | Projected | Worst case |  | Financial benefits | 250000
Value of benefits (total) | 250000 | 237000 | 225000 |  | Implementation cost (capex) | 100000
Achievability of benefits | Simple |  |  |  | Implementation cost (opex) | 70000
[5 empty] | Operational & overhead cost | 30000
EXPENSES (through 2024) | Best case | Projected | Worst case |  | Total cost | 200000
Implementation cost (capex) | 100000 | 106000 | 112000 |  | Financial return | 50000
Implementation cost (opex) | 70000 | 74000 | 78000
Operational and overhead cost | 30000 | 32000 | 34000
Total cost | 200000 | 212000 | 224000
Financial return | 50000 | 25000 | 1000
Achievability of delivery | Simple
An additional tool for calculating the number of workdays used for an activity. Use as needed.
[7 empty] | Senior staff HEW 10 | 177904.14
Estimate the number of workdays required | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Subtotal | National Manager | 165100
Days /week planned | 2.5 | 5 |  |  |  |  | Associate Director | 203200
Number of weeks | 11 | 12 |  |  |  | 23 | Director | 254000
Total workdays | 27.5 | 60 | 0 | 0 | 0 | 87.5
Note on K10: Mikail Ruutu: Professional staff. Paypoint 3, as of July 2019. With 27% on-costs. 2% annual increases as per the EBA.
Note on B17: Assumption based on typical 251 - 255 work days a year, less 4 weeks of annual leave, less potential individual days off.