## Instructions
ACU PROJECT BENEFITS REALISATION PLAN
This workbook is used to identify, plan and monitor the benefits enabled by a project.
They are the long-term changes resulting from delivering a change to how things are done and typically impact the ACU revenue or costs, staffing, service levels, etc.
This workbook is owned by the Executive Sponsor. It is used by the Benefit Owner(s) during the project to plan the benefits realisation, and after the project to record the actual realisation of benefits.
In Corporate Services the workbook is accessed by the Portoflio Projects Office (PPO) for on-going reporting of the benefits realisation in the portfolio.
GENERAL
Benefits are typically identified in an iterative manner in collaboration between all key stakeholders, led by the Executive Sponsor. This workbook is structured to support this approach. Key steps are identified below.
Information which goes into the Business Case:
1) Define the outcome, the associated benefit and the applicable measurement. 2) Identify the outputs (deliverables) required to achieve the outcome. If any of the outputs have an immediate benefit, define that together with the applicable measurement.
Benefits realisation plan, completed during the project Plan phase.
3) Define the action(s) required to achieve each benefit and confirm the Benefit Owner(s).
Tracking during and after the project implementation.
4) At set frequencies, perform measures to confirm the progress towards the benefits. Record the interim results, and eventually the final measurement result.
The project governance group (Executive Sponsor, Project Board, or Steering Committee) will need to agree to the benefits, and the Benefit Owner will need to be able to measure or develop a measure for the benefits they are accountable of.
An outcome typically has a single benefit recorded against it. If more than one benefit seem logical, you are likely to have secondary outcomes. Associate the most significant benefit with the primary outcome and any potential additional benefits to the respective secondary outcomes.
Fields on white background are input fields. Fields on grey background are links to other fields or calculations and locked from editing.
FIELDS USED
Identification
Objective - The task a project is set to achieve, e.g. 'To build a new process' or 'To add a new reporting module to LEO'.
Output - What the project delivers from it, a tangible and usable result from the work done. Typically this would be e.g. a new process (including the decriptions and instructions, flow diagrams, roles and responsibilities, etc), a business system or a module in it, a teaching or other space, etc.
Benefit - The title of a benefit (e.g. 'Equivalent full-time student load (EFTSL)' or 'Annual rental cost').
Measurement - How will progress of a benefit be measured? This often refers to a reading data from a system, a survey, report, sums or counts, etc.
Benefit class - Classification of each benefit. Financial and non-financial are measured with the progress and achievement shown over time. There are 8 benefit classes.
Priority - How important is an individual output to realising the outcome. This helps in prioritising the work if resources are constrained.
Realisation Plan
Action required - The key part of the benefits realisation plan. What action need to be taken to fully realise a benefit? This may refer to business change activities, decommissioning, or any other work that need to happen for the benefit to be realised.
Measurement Frequency - How often the measurement will be taken to monitor the realisation of the benefit? E.g. savings in annual recurring costs would be evidenced at the payment of the respective invoice, i.e. annually.
Benefit Owner - The Benefit Owner's role in the ACU organisation (e.g. "Deputy Dean, Health Sciences"). Each benefit has a single owner and they would typically be at the executive or senior management level who are accountable for the respective unit(s) in ACU. For benefits, they report to the Executive Sponsor.
Target date - When will the targeted value be achieved (month, year)? In case of an estimate at a quarterly or annual level, mark the last month of that time period (e.g. end of Semester 1/2019 would be "June 2019"). Typically the benefits realisation period should be set to maximum 1 year, unless the benefits take several years time to develop fully. In all cases, the realisation period should be limited to at most 3 years.
Target
Baseline - The current value of a benefit (e.g. current score of a survey question, current costs, throughput times of a process, etc). To provide a reliable comparison, it is measured the same way the realisation of the benefit is intended to be measured.
Baseline date - When is the benefit baseline taken (month, year)?
Best - The intended future value of a benefit if it can be fully realised. This target should be achievable within the timeframe set for it. Use precise figures, where possible (e.g. '$1,100,000' or '91%').
Projected - The future value of a benefit when it is realised taking into account the deduction in value if likely risks eventuate and the target is not met in full.
Worst - The future value of a benefit when it is realised taking into account the deduction in value if all risks eventuate and severely hinder the realisation of the benefit.
Results
Interim 1 / 2 / 3 - The value of the benefit at an interim measurement point. For each measurement, the value will be recorded. For any output benefits the final measure, and respectively for the outcome benefit the first measurement is done during the Post-implementation Review (PIR).
Final - The value of the benefit at the final measurement point. This is the value reported as the actual benefit realised through the change (project).
% of projected - An automatically calculated field to show how much of the projected benefit has been achieved. E.g. if the baseline was $200,000, target value $150,000 (a cost saving) and a measurement returns $180,000, the change would be 40% (intended change = $50,000 saving, of which $20,000 has now been achieved).

## Output benefits
OUTPUT BENEFITS
Benefits which will be realised during a project or at the completion of the implementation.
The final measurement values are presented in the PIR along with any recommendations on how to sustain the benefits achieved.
IDENTIFICATION | [5 empty] | REALISATION PLAN |  |  | TARGET |  |  |  |  | RESULTS
Objective | Output | Benefit | Measurement (benefit) | Benefit class | Priority | Actions required | Benefit Owner | Target date | Baseline | Baseline date | Best | Projected | Worst | Interim 1 | Interim 2 | Interim 3 | Final (PIR) | % of projected
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Outcome benefits
OUTCOME BENEFITS
Benefits which will be realised after the project completion through the adoption and use of the outputs.
The PIR will provide the first interim measure, and a benefit report is presented by the Executive Sponsor at the latest 12 months from the delivery of the final output.
Improved / maintained government funding revenue
Retain revenue
IDENTIFICATION |  |  |  | REALISATION PLAN |  |  |  | TARGET |  |  |  |  | RESULTS
Output | Measurement | Benefit class | Priority | Actions required | Measurement frequency | Benefit Owner | Target date | Baseline | Baseline date | Best | Projected | Worst | Interim 1 (PIR) | Interim 2 | Interim 3 | Final | % of projected
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Field values
DATA FIELD VALUES
This sheet contains values used in drop-downs and formulas in this workbook.
Please do not change these!
Benefit class | Note
F - IR | Increase revenue
F - RR | Retain revenue
F - AC | Avoid cost
F - RC | Reduce cost
N - ISU | Improve student experience
N - ISA | Improve staff experience
N - MSU | Maintain student experience
N - MSA | Maintain staff experience
N - CI | Catholic identity