## Instructions
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
Instructions
This Project Communications Plan template is intended to list all planned communication activities and meetings in a project.
All projects should aim to keep their stakeholders well informed. For this purpose, this template assists in identifying the key stakeholders and what communications are required with each.
Start by identifying the key stakeholders and their characteristics. Then you can plan for the relevant communication events and meetings to keep the stakeholders informed in a way which is most appropriate to them.
This plan should be reviewed periodically to confirm it corresponds with the potentially changing group of stakehodlers and their communication needs.
Scaling used when identifying stakeholders
Stakeholder's INTEREST in the project
1 | Not interested at all, indifferent, no impact to own work.
2 | Slight interest in overview, does not want to know more, little impact to own work.
3 | Reasonable interest, receptive, some change to own work.
4 | Wants to have deep understanding of the product and impacts, clear change to own work.
5 | Willing to champion, sees change crucial, may have big impact to own work.
Stakeholder's INFLUENCE on the project
1 | Has no access to influencal stakeholders or decision makers, viewpoints likely to be not heard.
2 | Has access to influencal stakeholders or decision makers, but limited influence over them.
3 | Can influence opinions, is listened to by stakeholders or decision makers.
4 | Opinion leader, has clear influence over other stakeholders or decision makers. Can effectively promote or hinder project or change.
5 | Champion, key decision-maker, respected leader or expert, others follow his lead. Can turn around or stop support for the project or change.
Stakeholder's SUPPORT of the project
1 | Negative towards the project / change, attempts to slow or stop progress. May want to drop out.
2 | Hesitant towards the project / change, may openly question it, stays on the sidelines without helping or hindering.
3 | Neutral, allows project / change to happen and supports it in principle but does not help it.
4 | Supportive, willing to help the project / change, understands the key benefits to own work.
5 | Champion, willing to go the extra mile and work with others to win them over, advocates the benefits to own and others' work.

## Stakeholders
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
Stakeholder identification
Key stakeholders in this project
Memberships (key audience groups)
Organisation | Role | Stakeholder name | Interest | Influence | Support | Governance | SME | Supplier | Impacted | Project support | Stakeholder's expectations from the project | Project's requirements from the Stakeholder | Comments
ACU | Provost |  | 3 | 3 | 1 |  |  |  | Impacted
ACU | Deputy Provost |  | 4 | 3 | 5 |  |  |  | Impacted
ACU | VC |  | 2 | 4 | 3 |  |  |  | Impacted
ACU | COO |  | 3 | 1 | 3 | Governance |  |  | Impacted
ACU | Deputy COO |  | 3 | 5 | 5 | Governance
ACU | Academic Registrar |  | 4 | 3 | 3 | Governance
ACU | Director MER |  | 1 | 3 | 3
ACU | CIO |  | 5 | 5 | 2 | Governance
ACU | Director SES |  | 3 | 3 | 1 |  |  |  | Impacted
ACU | Exec Dean FHS |  | 3 | 3 | 2 |  |  |  | Impacted
ACU | Exec Dean FLB |  | 5 | 2 | 2 |  |  |  | Impacted
ACU | Exec Dean FEA |  | 3 | 1 | 1 |  |  |  | Impacted
ACU | Exec Dean FTP |  | 3 | 2 | 1 |  |  |  | Impacted
ACU | SA Timetabling & Exams |  | 2 | 3 | 3 |  | SME
ACU | FHS faculty admin team |  | 3 | 1 | 4 |  | SME |  | Impacted
ACU | FLB faculty admin team |  | 3 | 1 | 4 |  | SME |  | Impacted
ACU | FEA faculty admin team |  | 3 | 1 | 4 |  | SME |  | Impacted
ACU | FTP faculty admin team |  | 3 | 1 | 4 |  | SME |  | Impacted
x | x | x | x | x | x | [5 empty] | x | x | x
Note on A7: Mark 'ACU' for internal stakeholders, and the organisation or company name for the external ones.
Note on D7: How interested is the stakeholder in the project or its success? 1 Not interested 2 Slight interest 3 Reasonable interest 4 Wants deep understanding 5 Willing to champion
Note on E7: How much can the stakeholder influence the project or decisions? 1 No access to influencers 2 Has access to influencers 3 Can influence opinions 4 Opinion leader 5 Champion or a key decision-maker
Note on F7: How much does the stakeholder support the project? 1 Negative 2 Hesitant 3 Neutral 4 Supportive 5 Champion
Note on G7: A member of the relevant Program Board, project governance, university governance (e.g. VCEB) or any other ACU forum which can directly influence the project. In a RASCI matrix, typically A or R roles.
Note on H7: Provides subject matter expertise to the project. In a RASCI matrix, typically C or S roles.
Note on I7: Supply goods or services to the project through a contractual arrangement or a PO. Marked S in a RASCI matrix, if included.
Note on J7: Those who are impacted by the project or its outputs. Often also called 'change target' or 'benefits recipient'. In a RASCI matrix, often marked as I.
Note on K7: Those who provide supporting services to the project, e.g. PMO / PPO services. In a RASCI matrix, often marked as C and I, if included.

## Stakeholder radar
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
Stakeholder radar

## Stakeholder matrix
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
Stakeholder matrix

## Messages
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
Key messages
Key messages or communication events in the project
Audience | Message | Purpose (objective) | Content (key messages) | Format | Frequency | Responsible | Review | Notes
Project Steering Committee | Project status | Inform the senior stakeholders, equip for decision-making. | PowerBI dashboard (PPM PSR): milestone calendar, achievements and future work, key financials, significant risks and issues, commentary and request for decisions. | Email | Monthly | Project Manager | (no review) | Project data in PPM updated by the start of 4th business day of each month.
x | x | x | x | x | x | x | x | x

## Meetings
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
Regular meetings
Regular meetings or events in the project
Regular schedule
Event | Content | Participants | Location | Mon | Tue | Wed | Thu | Fri | Notes
Project Steering Committee | Project direction, progress of milestones and project outputs, significant risks / issues, customer expectations. | Executive Sponsor, Steering Committee members, Project Manager (presenting). | Teams |  | 2-3 pm (1st / 3rd Tue of month)
x | x | x | x | x | x | x | x | x | x
Note on G6: Mikail Ruutu: When does each meeting or event take place?
Note on A7: Meeting or event name (title), e.g. "Project Board".
Note on B7: Key agenda items, discussion points or expected results.
Note on C7: Who is expected to regularly attend? The event leader / meeting chair / facilitator is bolded.
Note on D7: The meeting room names. For virtual meetings, use 'Teams'.

## Data gathering
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
Data gathering
Data required for effective project communications.
Purpose | Data required | Timeframe | Frequency | Provided by… | Delivered to… | Format | Comments
x | x | x | x | x | x |  | x

## RASCI matrix
PROJECT STAKEHOLDER MANAGEMENT AND COMMUNICATIONS
RASCI matrix
STAKEHOLDERS & RESPONSIBILITIES
Role | Name | Interest | Influence | Directing the project | Scope & schedule | Risks & issues | Project documents | Gating | Business need & requirements | Data definitions & integrations | System install & config | Training | Handover
Provost |  | 3 | 3 | I | I | I
Deputy Provost |  | 4 | 3 | I | I | C |  |  | C |  |  | I | I
VC |  | 2 | 4 | I | I | I
COO |  | 3 | 1 | A | I | I | I | I | I | I |  |  | I
Deputy COO |  | 3 | 5 | C | I | I | [6 empty] | I
Academic Registrar |  | 4 | 3 | C | C | C |  |  | A | A | I | I | I
Director MER |  | 1 | 3 | C | C | C |  |  |  |  | I | I | I
CIO |  | 5 | 5 | R | A | A | A | A | I | I | I | I | A
Director SES |  | 3 | 3
Exec Dean FHS |  | 3 | 3 | C | C | C | I |  | S | S | I | C | C
Exec Dean FLB |  | 5 | 2
Exec Dean FEA |  | 3 | 1
Exec Dean FTP |  | 3 | 2
SA Timetabling & Exams |  | 2 | 3 | S | C | C |  |  | S | S | I | C | C
FHS faculty admin team |  | 3 | 1 | S | C | C |  |  | S | S | I | C | C
FLB faculty admin team |  | 3 | 1
FEA faculty admin team |  | 3 | 1
FTP faculty admin team |  | 3 | 1
Project Manager |  | 5 | 3 | C | R | R | R | R | C | C | A | A | R
Business Analyst |  | 3 | 2 |  | S | C | S | C | R | S |  | S | C
Technical Lead |  | 3 | 2 |  | S | C | S | C | S | R | R | S | S
Business Change Manager |  | 3 | 2 | [8 empty] | R | S
RASCI
Responsible
Accountable
Support
Consulted
Informed
Note on A42: Mikail Ruutu: Those who do the work to achieve the task.
Note on A43: Mikail Ruutu: The one ultimately answerable for the correct and thorough completion of the deliverable or task, and the one from whom responsible is delegated the work. In other words, an accountable must sign off (approve) on work that responsible provides. There must be only one accountable specified for each task or deliverable.
Note on A44: Mikail Ruutu: Resources allocated to responsible to assist in completing the task.
Note on A45: Mikail Ruutu: Those whose opinions are sought, typically subject matter experts.
Note on A46: Mikail Ruutu: Those who are kept up-to-date on progress, often only on completion of the task or deliverable.