## Instructions
ACU PROJECT BENEFITS REALISATION PLAN
This workbook is used to identify, plan and monitor the benefits enabled by a project. It should be started while preparing a Project Business Case.
The workbook is owned by the Executive Sponsor. It is used by the Benefit Owner(s) during the project to plan the benefits realisation, and after the project to record the actual realisation of benefits.
In Corporate Services the workbook is accessed by the Portoflio Projects Office (PPO) for on-going reporting of the benefits realisation in the portfolio.
Please refer to the ACU Project Management Model > 'Benefits management for projects' for more information (https://staff.acu.edu.au/our_university/projects/benefits_management_for_projects).
STEPS IN GENERAL
Benefits are typically identified in an iterative manner as a collaboration between all key stakeholders, led by the Executive Sponsor. This workbook is structured to support this approach. Key steps are identified below.
1) Before creating a Proposal for Business Change, the Executive Sponsor has created a Benefit Map.
2) While preparing the Project Business Case, the Executive Sponsor transfers information from the Benefit Map onto this workbook (fields 'Objective', 'Output' and 'Benefit category' for output benefits; 'Outcome' and 'Benefit category' for outcome benefit). The remaining information for the Identification and Target sections are added.
The information required in the Project Business Case: A) The outcome, the associated benefit category and the applicable measurement, and the target value. B) The objectives and outputs (deliverables) required to achieve the outcome, along with the measurement and target values.
3) After the approval of the Project Business Case, the Benefit Owner(s) adds the Realisation Plan section. This outlines the action to be taken to achieve each benefit. This work should be done in collaboration with the Business Change Manager and the Project Manager.
Please note: Those output benefits which require further action before the outcome is fully realised are replicated onto the Outcome Benefit worksheet. The relevant follow-on actions are planned for each output to ensure the outcome will be fully realised.
4) When the project implementation commences, the Benefit Owner(s) start to regularly monitor and measure the progress of the benefits. Interim measurement results are recorded in the workbook.
An outcome typically has a single benefit recorded against it. If more than one benefit seem logical, you are likely to have secondary outcomes. Associate the most significant benefit with the primary outcome and any potential additional benefits to the respective secondary outcomes. Expand the worksheet, as applicable.
SECTIONS AND FIELDS USED
Fields on white background are input fields. Fields on a coloured background are links to other fields or calculations and locked from editing.
Identification
Objective - The task a project is set to achieve, e.g. 'To build a new process' or 'To add a new reporting module to LEO'.
Output - What the project delivers from it, a tangible and usable result from the work done. Typically this would be e.g. a new process (including the decriptions and instructions, flow diagrams, roles and responsibilities, etc), a business system or a module in it, a teaching or other space, etc. Outcome - Expresses the future state after the chagne has been completed.
Benefit - The title of a benefit (e.g. 'Equivalent full-time student load (EFTSL)' or 'Annual rental cost').
Measurement - How will progress of a benefit be measured? This often refers to a reading data from a system, a survey, report, sums or counts, etc.
Benefit category - Categorisation of each benefit. Financial and non-financial are measured with the progress and achievement shown over time. There are 7 benefit categories (4 financial, 3 tangible).
Priority - How important is an individual output to realising the outcome. This helps in prioritising the work if resources are constrained.
Target
Baseline - The current value of a benefit (e.g. current score of a survey question, current costs, throughput times of a process, etc). To provide a reliable comparison, it is measured the same way the realisation of the benefit is intended to be measured.
Baseline date - When is the benefit baseline taken (month, year)?
Best - The intended future value of a benefit if it can be fully realised. This target should be achievable within the timeframe set for it. Use precise figures, where possible (e.g. '$1,100,000' or '91%').
Note about financial benefits: You need to add the best cases to the Project Financial Model and provide an annual breakdown of how much of each benefit is achieved per year (cumulative).
Projected - The future value of a benefit when it is realised taking into account the deduction in value if likely risks eventuate and the target is not met in full.
Worst - The future value of a benefit when it is realised taking into account the deduction in value if all risks eventuate and severely hinder the realisation of the benefit.
Realisation Plan
Actions required - The key part of the benefits realisation plan. What actions need to be taken to fully realise a benefit? This may refer to business change activities, decommissioning of old systems, or any other work that need to happen for the benefit to be realised.
Measurement Frequency - How often or when the measurement will be taken to monitor the realisation of the benefit? E.g. savings in annual recurring costs would be evidenced at the payment of the respective invoice, i.e. annually. Or a custom survey may be run e.g every two months.
Benefit Owner - The Benefit Owner's role in the ACU organisation (e.g. "Deputy Dean, Health Sciences"). Each benefit has a single owner and they would typically be at the executive or senior management level who are accountable for the respective unit(s) in ACU. For benefits, they report to the Executive Sponsor.
Target date - When will the targeted value be achieved (month, year)? In case of an estimate at a quarterly or annual level, mark the last month of that time period (e.g. end of Semester 1/2022 would be "June 2022"). Typically the benefits realisation period should be set to maximum 1 year, unless the benefits take several years time to develop fully. In all cases, the realisation period should be limited to at most 3 years.
Results
Interim 1 / 2 / 3 - The value of the benefit at an interim measurement point. For each measurement, the value will be recorded. For any output benefits the final measure, and respectively for the outcome benefit the first measurement is done during the Post-implementation Review (PIR).
Final - The value of the benefit at the final measurement point. This is the value reported as the actual benefit realised through the change (project).
% of projected - An automatically calculated field to show how much of the projected benefit has been achieved. E.g. if the baseline was $200,000, target value $150,000 (a cost saving) and a measurement returns $180,000, the change would be 40% (intended change = $50,000 saving, of which $20,000 has now been achieved).

## Output benefits
OUTPUT BENEFITS
Benefits which will be realised during a project or at the completion of the implementation.
The final measurement values are presented in the PIR along with any recommendations on how to sustain the benefits achieved.
Project name
Forecast completion
IDENTIFICATION | Objective
Output
Benefit
Measurement (benefit)
Benefit category
Priority
TARGET | Baseline
Baseline date
Best
Projected
Worst
REALISATION PLAN | Actions required
Measurement frequency
Benefit Owner
Target date
RESULTS | Interim 1
Interim 2
Interim 3
Final (PIR)
| % of projected | 0% | 0% | 0% | 0%
Outputs which require further action for the achievement of the outcome, are copied to the Outcome Benefits worksheet.

## Outcome benefit
OUTCOME BENEFITS
The long-term benefit which will be realised after the project completion through the adoption and use of the outputs.
The PIR will provide the first interim measure, and a Benefit Realisation Report is presented by the Executive Sponsor at the latest 12 months from the delivery of the final output.
| Project name | 0
Project completion
Outcome achieved
IDENTIFICATION | Objective | 0 | 0 | 0 | 0
| Output | 0 | 0 | 0 | 0
REALISATION PLAN | Actions required
Benefit Owner
Target date
OUTCOME
IDENTIFICATION | Outcome
Benefit
Measurement
Benefit category
TARGET | Baseline
Baseline date
Best
Projected
Worst
RESULTS | Interim 1
Interim 2
Interim 3
Final (Benefits Report)
| % of projected | 0%
Completion of the actions will result in the realisation of the outcome

## Field values
DATA FIELD VALUES
This sheet contains values used in drop-downs and formulas in this workbook.
Please do not change these!
Benefit categories | Note
Increase revenue $ | Improve financial position by increasing revenue.
Reduce cost $ | Improve financial position by reducing cost.
Repurpose $ | Move resources to other uses.
Secure $ | Secure revenue against loss, or expenses against increase.
Student experience | Improve or maintain student experience.
Staff experience | Improve or maintain staff experience.
Reputation | Improve ACU’s position as an academic institution.