## Instructions
INSTRUCTIONS FOR THE PROJECT ASSESSMENT
WHY
This assessment indicates the likely attractiveness and achievability of a proposed change or project.
It shows the strength of the proposal, and our confidence for fully achieving the desired outcome.
The results are used to inform the approval and funding decisions and governance arrangements.
The project category is always agreed to with the Executive Sponsor and the Portfolio Projects Office (PPO), using the information in this assessment.
A preliminary agreement is made before the submission of a Proposal for Business Change and finalised before the submission of a Project Business Case.
GENERAL
The assessment is done in two stages:
1) When a new change / project idea is submitted, the Service Improvement Team performs an initial triage.
The triage relies on an interview with the Executive Sponsor and a checklist, but can also use the early assessment from this workbook.
2) The early assessment is completed when developing a Proposal for Business Change.
In that document, the initial complexity level (simple, medium, complex) is based on the potential magnitude.
3) The full assessment is completed when preparing a Project Business Case and any time it is modified.
At that time, you can also review the early assessment and adjust any of the scores based on new information.
The resulting scores are shown on the 'Results' sheet.
When the most right-hand option is selected in any question, that aspect is a potential risk to the benefits or delivery. In this case, an action or mitigation plan is recommended.
HOW TO?
Enter the project or change name to the top of the Early assessment worksheet (cell C2).
In both assessments, enter your selected choice (a, b, c or d) in column F, next to the answer options.
The early assessment selections will influence the total score even when you've completed the full assessment part.
Once you have a Financial Model for the (potential) project, enter the value of financial benefits and project expenses from the Results to cells D11:D12 in the Financial Summary.
USING THE RESULTS
The score in cell I7 is used for project prioritisation in a Program Board.
The complexity rating in cell G8 guides in the governance model to be applied.
The radar chart under the results is copied into the Project Business Case, Project Outline section.
The confidence ratings are copied to the Project Financial Model (top of Project Cost Estimate worksheet).
RESULTING PROJECT CATEGORIES
The achievability rating is the primary score used to estimate the category but the final determination uses all the information in the assessment.
Simple - High confidence in delivering the project and achieving benefits. Low risk, low complexity, single stage. Mostly operationally funded, typically max $250K. Rating 76-100%.
--> Governed by the Executive Sponsor (1). Financial model can be developed by the sponsor and SME's but is reviewed by Finance.
Medium - Moderate confidence. Moderate risk, can be high complexity. Often a mix of operational and capital funding, max $2M (for all project stages). Rating 51-75%.
--> Governed by a Project Board (3). Financial model is guided and reviewed by Finance, please engage them at the latest when starting to develop a Project Business Case.
Complex - Low confidence. High risks, high complexity. Usually majority or completely capital funded, can be above $2M (for all project stages). Rating 15-50%.
--> Governed by a Steering Committee (7). Financial model is developed by Finance, please engage them at the latest when starting to develop a Project Business Case.

## Early assessment
|  | PROJECT ASSESSMENT |  |  |  | Early assessment
<Project name>
This assessment is done while preparing a Proposal for Business Change.
It gives an early indication of the value of a proposed change ("attractiveness").
CONTRIBUTION TO ACU GOALS | A | B | C | D | Your selection | Comments | Score | A | B | C | D | % in group | % overall
Contribution to priorities | None | PF, local priority | Strat Plan goal | Compliance |  |  | 9 | 0 | 3 | 6 | 9 | 23.08% | 9.89%
Improvement to student experience | No change | Adjust | Change | New service |  |  | 6 | 0 | 2 | 4 | 6 | 15.38% | 6.593%
Improvement to staff experience | No change | Adjust | Change | New service |  |  | 3 | 0 | 1 | 2 | 3 | 7.692% | 3.297%
Improvement to operational efficiency | No change | Slight | Measurable | Significant |  |  | 9 | 0 | 3 | 6 | 9 | 23.08% | 9.89%
Broadness of impact | Local | Faculty / Dir | Portfolio | All / national |  |  | 4 | 1 | 2 | 3 | 4 | 10.26% | 4.396%
Ability to recycle / reuse existing assets or resources | New resources | Partially | Recycle existing | Unused get used |  |  | 8 | 0 | 2 | 5 | 8 | 20.51% | 8.791%
100%
MAGNITUDE | A | B | C | D | Your selection | Comments
Process / work practice / service changes | Remains as is | Adjust | Change | Redesign / new |  |  | 4 | 1 | 2 | 3 | 4 | 15.38% | 4.396%
System to be implemented | No system | Single function | Multi-function | Core system |  |  | 4 | 0 | 1 | 3 | 4 | 15.38% | 4.396%
Level of current uncertainties | We know this well | Some questions | Known unknowns | "Don't know" |  |  | 4 | 0 | 1 | 2 | 4 | 15.38% | 4.396%
Contractors and capital-funded staff share of work | < 25% | < 50% | < 75% | > 75% |  |  | 4 | 1 | 2 | 3 | 4 | 15.38% | 4.396%
Expected duration | < 6 mo | < 12 mo | < 18 mo | > 18 mo |  |  | 4 | 1 | 2 | 3 | 4 | 15.38% | 4.396%
Capacity available | Available | We can buy | Small gaps / delay | Major gaps / delay |  |  | 6 | 1 | 2 | 4 | 6 | 23.08% | 6.593%
|  |  |  | Potential complexity level |  |  | 100%
CONFIDENCE IN REALISING THE BENEFITS | A | B | C | D | Your selection | Action / mitigation of high risks
Complexity of process changes (outputs) to be implemented | Easy | Well defined | Moderate | Complex |  |  | 4 | 1 | 2 | 3 | 4 | 15.38% | 4.396%
Outcome's impact on stakeholders | Improves work | Neutral | Have questions | Some may hesitate |  |  | 6 | 1 | 2 | 4 | 6 | 23.08% | 6.593%
Time required to convert project outputs into the final outcome | ≤ 3 mo | ≤ 6 mo | ≤ 1 year | > 1 year |  |  | 4 | 1 | 2 | 3 | 4 | 15.38% | 4.396%
Number of stakeholder groups involved | 1 | 2 - 3 | 4 - 5 | 6 or more |  |  | 8 | 0 | 2 | 5 | 8 | 30.77% | 8.791%
Size of total financial benefits (over 5 years) | > $1M | $251K - $1M | $51K - $250K | ≤ $50K |  |  | 4 | 1 | 2 | 3 | 4 | 15.38% | 4.396%
15.38%
Note on I8: Mikail Ruutu: The scoring of this row updated in version 2023 06 to match the UPMO / IMC assessment scoring.
Note on I11: Mikail Ruutu: The scoring of this row updated in version 2023 06 to match the UPMO / IMC assessment scoring.

## Full assessment
|  | PROJECT ASSESSMENT |  |  |  | Full assessment
<Project name>
This assessment is done while preparing a Project Business Case.
It characterises the value of the change ("attractiveness") and estimates the complexity of the delivery ("achievability").
CONTRIBUTION TO ACU GOALS | A | B | C | D | Your selection | Comments | Score | A | B | C | D | % in group | % overall
Expected benefits | Non-financial | Benefit $ < cost | Profitable years 2-3 | Profitable in year 1 |  |  | 9 | 0 | 3 | 6 | 9 | 27.27% | 7.317%
Evidence of need | None | Anecdotal | Tangible | Detailed |  |  | 3 | 0 | 1 | 2 | 3 | 9.091% | 2.439%
Mitigate risk, maintain compliance, or improve OHS | No impact | Contribute | Mitigate | Eliminate |  |  | 6 | 0 | 2 | 4 | 6 | 18.18% | 4.878%
Urgency to start | Timing flexible | Can wait 1 y | Can wait 6 mo | Critical |  |  | 9 | 0 | 2 | 5 | 9 | 27.27% | 7.317%
Stakeholder readiness | To be assessed | Change identified | Will be ready | All ready |  |  | 6 | 0 | 2 | 4 | 6 | 18.18% | 4.878%
100%
CONFIDENCE IN REALISING THE BENEFITS | A | B | C | D | Your selection | Action / mitigation of high risks | Score | A | B | C | D | % in group | % overall
Executive Sponsor's experience in similar projects | Extensive | Comparable | Some | None |  |  | 4 | 1 | 2 | 3 | 4 | 25% | 3.252%
Overall complexity of the desired outcome | Simple | Some changes | Extensive | Complex |  |  | 4 | 1 | 2 | 3 | 4 | 25% | 3.252%
Work required to convert project outputs into the final outcome | Simple | Some changes | Extensive | Complex |  |  | 4 | 1 | 2 | 3 | 4 | 25% | 3.252%
Number of benefit owners involved | 1 | 2 – 3 | 4 - 5 | 6 or more |  |  | 4 | 1 | 2 | 3 | 4 | 25% | 3.252%
15.38%
CONFIDENCE IN DELIVERING THE PROJECT | A | B | C | D | Your selection | Action / mitigation of high risks | Score | A | B | C | D | % in group | % overall
Impact on students (while delivering) | None | Some changes | Extensive | Complex | A |  | 0 | 0 | 2 | 3 | 4 | 5.405% | 3.252%
Impact on staff (while delivering) | None | Some changes | Extensive | Complex |  |  | 4 | 0 | 2 | 3 | 4 | 5.405% | 3.252%
Impact on external partners (while delivering) | None | Some changes | Extensive | Complex |  |  | 4 | 0 | 2 | 3 | 4 | 5.405% | 3.252%
Number of key stakeholders or groups impacted | 1 | 2 – 3 | 4 - 5 | 6 or more |  |  | 8 | 1 | 2 | 5 | 8 | 10.81% | 6.504% | Studies and experience tells this factor is much more significant for success than many others.
Changes to procedures, processes or work practices? | None | Some changes | Extensive | Complex |  |  | 4 | 0 | 2 | 3 | 4 | 5.405% | 3.252%
Overall complexity of the outputs | Simple | Some changes | Extensive | Complex |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
Level of innovation expected | None | Some features | New to ACU | New to sector |  |  | 4 | 0 | 2 | 3 | 4 | 5.405% | 3.252%
Interfacing expected with or impacts (dependencies) to other systems / products | None | Simple | Few | Complex |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
Future process collects, uses, stores or discloses personal information? | None | Personal | Sensitive | Health information |  |  | 6 | 1 | 3 | 4 | 6 | 8.108% | 4.878%
ACU familiarity with the potential product / system type? | Extensive | Comparable | Some | None |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
How good fit or match to ACU are the solutions available to us? | 90% | 75% | 50% | 25% |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
Confidence that the right resources are available | Secured | High | Medium | Low |  |  | 8 | 1 | 2 | 5 | 8 | 10.81% | 6.504% | Studies and experience tells this factor is much more significant for success than many others.
Stability of requirements | Mandated | Stable | Average | Unstable |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
Delivery schedules / deadlines | Free | Flexible | Firm | Mandated |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
Likely duration of the implementation (until project closure) | ≤ 6 mo | 6 - 12 mo | 1 - 2 years | 2+ years |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
Cost level of the impementation | ≤ $150 K | ≤ $250 K | ≤ $2 M | $2+ M |  |  | 4 | 1 | 2 | 3 | 4 | 5.405% | 3.252%
15%
Note on I8: Mikail Ruutu: The answer options and scoring of this row updated in version 2023 06 to match the UPMO / IMC assessment scoring.

## Results
|  |  |  | PROJECT ASSESSMENT |  |  |  |  | Results
|  |  |  | <Project name> |  |  |  |  | For a Project Business Case
CONTRIBUTION |  |  |  | 100% | [5 empty] | Copy the cells B6:F14 to the Project Business Case
Contribution to priorities |  |  |  | #N/A | #N/A |  |  |  |  | > end of 'Executive Summary'.
Improvement to student experience |  |  |  | #N/A | #N/A
Improvement to staff experience |  |  |  | #N/A | #N/A
Improvement to operational efficiency |  |  |  | #N/A | #N/A
Broadness of impact |  |  |  | #N/A | #N/A
CONFIDENCE RATINGS in success |  |  | Score | Complexity
Benefits (value to the University) |  |  | 15.38% | Complex | [5 empty] | Copy the cells E13:E14 to the Project Financial Model
Delivery (complexity of the delivery) |  |  | 15% | Complex | [5 empty] | > 'Financial Summary' cells D10:D11.
Contribution | Benefits $M | Benefits % |  | Cost $M | Capacity | Delivery % | ROI | Score | Comments
100% | #REF! | 15.38% |  | #REF! | 16.67% | 15% | #REF! | #REF!

## UPMO & IMC assessment
THIS WORKSHEET IS USE FOR PROJECT PRIORITISATION BY THE UPMO AND IMC.
<Project name>
PRIORITY SCORE |  | Points | Comments
Contribution to priorities
Improvement to operational efficiency
Financial contribution
0
MERIT SCORE |  | Points | Comments
Ability to recycle / reuse existing assets or resources
Improvement to student experience
Improvement to staff experience
Broadness of impact
0
Total score: |  | 0
UPMO recommendation: |  | Please defer to later
Portfolio project list scoring
From Financial Model |  |  | Comments
Benefits $ |  | 0
Cost $ |  | 0
Cost/benefit ratio | 40% | #DIV/0!
From Project Assessment | Weight | Results | Comments
Contribution % | 40% | 100%
Confidence benefits | 10% | 15.38%
Confidence delivery | 10% | 15%
Cost/benefit |  | #DIV/0!
Contribution |  | 40%
Benefits |  | 1.538%
Delivery |  | 1.5%
SCORE |  | #DIV/0!

## Definitions
EXPLANATIONS TO THE QUESTIONS IN THE ASSESSMENT
CONTRIBUTION TO ACU GOALS
The strength of the Proposal | Option A | Option B | Option C | Option D
Contribution to priorities | None - The change is not linked to any of ACU's expressed goals or priorities. | PF, local priority - Implements a portfolio or local level priority, or enables other projects to implement priorities or strategic goals. | Strat Plan goal - Directly contributes to an ACU Strategic Plan 2023 goal (e.g. 2.2) or implements a VC Annual Priority focus area. | Compliance - Mandatory for regulatory or WHS compliance reasons. Please reference the respective regulation or policy.
Improvement to student experience | No change - This change is not expected to alter the student experience. | Adjust - A refinement of an existing student experience or service. | Change - A distinct change or addition to an existing student experience or service. | New service - Developing new or redesigning experiences or services, transforming what is offered in an area.
Improvement to staff experience | No change - This change is not expected to alter the staff experience. | Adjust - A refinement of an existing staff experience or service. | Change - A distinct change or addition to an existing staff experience or service. | New service - Developing new or redesigning experiences or services, transforming what is offered in an area.
Improvement to operational efficiency | No change - This change is not expected to improve the current operational efficiency, or the improvement is hard to measure. | Slight - Slight improvement in operations. Change 1 - 10% in time or cost of a service of function. | Measurable - Measurable adjustments in operations. Change 11 - 20% in time or cost of a service of function. | Significant - Significant improvement in operations through a changed process or system. The service capacity changes significantly, more than 20% in time or cost of the service of function.
Broadness of impact | Local - Students in a faculty / school or staff on campus, or staff at a unit level (org unit level 4 or below). | Faculty / Dir - Single faculty / school or Directorate nationally (org unit level 3). | Portfolio - Students in multiple faculties or state-wide (e.g. MEL & BAL), or a portfolio nationally. | All / national - All students or all staff nationally.
Ability to recycle / reuse existing assets or resources | New resources - This outcome creates a need for new resources in the university. | Partially - The outcome can reuse some of the existing resources but will require also some new resources. | Recycle existing - The outcome will reuse existing resources in the university, putting them into a better use. | Unused get used - The outcome will take into use existing resources which are currently unused or heavily underutilised.
MAGNITUDE
The expected size of the change | Option A | Option B | Option C | Option D
Process / work practice / service changes | Remains as is - The processes, work practices or services are expected to remain completely in their current state. | Adjust - The processes, work practices or services will be slightly adjusted. E.g. some activities in a process are altered but the main flow remains similar. | Change - The processes, work practices or services will be clearly changed. This may involve changed tasks or skills for staff, or new ways to deliver a service. | Redesign / new - The processes, work practices or services are redesigned and will change significantly. The future tasks or expected knowledge / skills will clearly differ from the current state.
System to be implemented | No system - This is a process or practice change with no impact to any of the current systems. | Single function - A system for 1-2 dedicated functions is implemented. | Multi-function - A system with several functions is implemented. The functions typically cover multiple units in ACU. | Core system - A centralised core system which underpins multiple services (similar to Aurion, Banner, LEO, etc).
Level of current uncertainties | We know this well - The change is well defined and already analysed. There are no open questions or uncertainties. | Some questions - The change is generally understood but some questions still remain to be answered. | Known unknowns - The change is outlined but there are several significant aspects still to resolve. However, those aspects have been identified. | "Don't know" - While we know what is needed, there are likely to be aspects we are yet to discover and resolve.
Contractors and capital-funded staff share of work | < 25% - Under 25% of the work effort is likely to be done using external contractors or capital-funded staff. | < 50% - 25% - 50% of the work effort is likely to be done using external contractors or capital-funded staff. | < 75% - 50% - 75% of the work effort is likely to be done using external contractors or capital-funded staff. | > 75% - More than 75% of the work effort is likely to be done using external contractors or capital-funded staff.
Expected duration | < 6 mo - The project to implement outputs can be carried out in less than 6 months. | < 12 mo - The project to implement outputs is likely to take 6 - 12 months. | < 18 mo - The project to implement outputs is likely to take 12 - 18 monts. | > 18 mo - The project to implement outputs is likely to take more than 18 monts.
Capacity available | Available - The required expertise and staff is already available in ACU. Their engagement to the project may need to be negotiated. | We can buy - The required expertise and staff is either available in ACU or can easily be hired or sourced through agencies. | Small gaps / delay - We are likely to have some gaps in the expertise and staff required for the project. It may take time or increased cost to fill those gaps. | Major gaps / delay - We currently have clear gaps in the expertise and staff required for the project. Sourcing that expertise may take time or significant added cost.
CONFIDENCE IN REALISING THE BENEFITS
| Option A | Option B | Option C | Option D
Complexity of process changes (outputs) to be implemented | Easy - Proposed changes to the current process or work practices are small and can be seen as adjustments to the current. They are easy to adopt. | Well defined - Proposed changes to the process or work practices change some tasks or skills required. They are well defined and easy to train. | Moderate - Proposed changes to the process or work practices bring in a clearly different way of doing some tasks and designing the new is likely to require negotiation. | Complex - The design of future process or work practices is complicated and changes made to the current are significant. This often would involve a complex current processes.
Outcome's impact on stakeholders | Improves work - The changes are seen as positive steps forward in how the impacted stakeholders work or interact. | Neutral - The changes may get either a slightly mixed reception or the impacted stakeholders may not need to pay much attention to them. | Have questions - The changes may be questioned by some of the impacted stakeholders. This generally is to seek more information and assurance before accepting them. | Some may oppose - It is likely that at least some stakeholders would see changes being adverse and are likely to either oppose them or attempt to revert back to the current model.
Time required to convert project outputs into final outcome | ≤ 3 Mo - The final outcome can be reached within three months from the delivery of final output. | ≤ 6 Mo - The final outcome can be reached within six months from the delivery of final output. | ≤ 1 Year - The final outcome can be reached within 3 - 12 months from the delivery of final output. | > 1 Year - Reaching the final outcome is likely to take more than a year from the delivery of final output.
Number of stakeholder groups involved | 1 - There is one stakeholder (or group) involved in the work to convert the outputs into the outcome and realise benefits. They are outside of the immediate team(s) using the outputs. | 2 - 3 - There are 2 -3 stakeholders (or groups) involved in the work to convert the outputs into the outcome and realise benefits. They are outside of the immediate team(s) using the outputs. | 4 - 5 - There are 4 - 5 stakeholders (or groups) involved in the work to convert the outputs into the outcome and realise benefits. They are outside of the immediate team(s) using the outputs. | 6 or more - There are 6 or more stakeholders (or groups) involved in the work to convert the outputs into the outcome and realise benefits. They are outside of the immediate team(s) using the outputs.
Size of total financial benefits (over 5 years) | > $1Mill - The expected financial benefits (revenue and/or savings) total at least $1M over the life of the solution (max five years). | $251K - $1M - The expected financial benefits total at least $251K, up to $1M, over the life of the solution (max five years). | $51K - $250K - The expected financial benefits total at least $51K, up to $250K, over the life of the solution (max five years). | < $50K - The expected financial benefits are max $50K over the life of the solution (max five years) -or- all benefits are non-financial.
ADDITIONAL QUESTIONS IN THE FULL ASSESSMENT
CONTRIBUTION TO ACU GOALS
The strength of the Business Case | Option A | Option B | Option C | Option D
Expected benefits | Intangible - Benefits are not measurable or no benefits identified for the proposed change. | Non-financial - Measurable non-financial benefits identified. They would relate to the student of staff experience or ACU's reputation. | Cost ≥ benefit - Financial benefits where costs (over 5y) equal or exceed the value of benefits. | Benefit > cost - The value of financial benefits exceed costs (over 5y). This results in a payback.
Evidence of need | None - The business need lacks supporting evidence and can be seen as a suggestion to change a service, process or system. | Anecdotal - The business need has anecdotal support or follows from a discussion minuted in a management, executive or a committee meeting. | Tangible - The business need is supported by surveys, repeated requests from service users (written or in a system), local or ACU leadership priorities, or similar tangible evidence. | Detailed - Mandatory, or the business need is strongly supported by unambiguous evidence, e.g. statistically sound and robust surveys, process cycle time analysis, or similar.
Mitigate risk, maintain compliance, or improve OHS | No impact - No impact to ACU's risk position or compliance, or improvement in OHS. | Contribute - Contribute to an improvement in ACU's risk position, compliance or OHS but not sufficient alone to change the position. | Mitigate - Significant improvement of risk position, compliance or OHS but some residual risk or issues will remain. | Eliminate - Addresses a risk, compliance or WHS issue completely, eliminating it altogether.
Urgency to start | Timing flexible - The work can be scheduled to commence flexibly whenever resources and funding can be made available, even if this might lead to a significant wait. | Can wait 1 y - The work can be scheduled to commence within the next year without a significant impact to ACU's services. | Can wait 6 mo - The work can be scheduled to commence within the next six months without a significant impact to ACU's services. | Critical - The work needs to commence as soon as possible and completed with urgency due to unexpected regulatory or similar changes in ACU's operating environment and tight external timelines posed to the University.
Stakeholder readiness | To be assessed - The readiness of the impacted stakeholders is yet to be assessed. | Change identified - What will change with each stakeholder (group) has been identified. The assessment of how ready they will be to adopt the new work practices, processes, skills or behaviours is yet to be done. | Will be ready - Changes to stakeholders' work and skills have been identified and any preparations outside of this project have been planned and can be completed in parallel of this project. | All ready - All stakeholders are already ready or are currently preparing to start with the new processes, work practices, skills or behaviours.
CONFIDENCE IN REALISING THE BENEFITS
| Option A | Option B | Option C | Option D
Executive Sponsor's experience in similar projects | Extensive - The Exec Sponsor has sponsored similar projects earlier, possibly multiple, and understand the work and potential challenges involved. | Comparable - The Exec Sponsor has sponsored related or comparable projects earlier, possibly multiple. They have a general appreciation of the work and potential challenges involved. | Some - The Exec Sponsor has sponsored some comparable projects, or been involved in a similar project as a key stakeholder. | None - This is the first project of this kind for the Exec Sponsor as a sponsor. Any potential projects they have sponsored earlier have been of a different nature.
Overall complexity of the desired outcome | Simple - Once the outputs have been delivered, it will be straighforward and easy to reach the outcome. | Some changes - Once the outputs have been delivered, action is required, often across multipe teams to achieve the intended outcome. This often involves reinforcing the change and training, and embedding new work practices. | Extensive - Once the outputs have been delivered, extensive dedicated action is required, often across multipe teams to achieve the intended outcome. This often involves repeated reinforcing the change and training, and embedding new work practices. | Complex - Once the outputs have been delivered, significant action is still required across multipe teams to achieve the intended outcome. This involves continuous reinforcing of the change and training, embedding new work practices, and perhaps further adjustments to roles, processes or systems.
Work required to convert outputs into outcome | Simple - It is likely the outcome can be achieved with some simple and well-known steps. | Some changes - The work after receiving project outputs until the outcome has been achieved is likely to require some work or adjustments to work practices, expected skills or behaviours. | Extensive - The work after receiving project outputs until the outcome has been achieved is likely to require multiple work streams or clear changes to work practices, expected skills or behaviours. | Complex - The work to achieve the outcome will require multiple work streams and major or complicated changes to work practices, expected skills or behaviours.
Number of benefit owners involved | 1 - All benefits are managed and reported on by a single Benefit Owner. | 2 – 3 - There are 2- 3 Benefit Owners assigned to the project (one owner per benefit). | 4 – 5 - There are 4- 5 Benefit Owners assigned to the project (one owner per benefit). | 6 or more - There are six or more Benefit Owners in the change. This also implies five or more outputs contributing to the outcome.
CONFIDENCE IN DELIVERING THE PROJECT
| Option A | Option B | Option C | Option D
Impact on students (while delivering) | Minimum - During the delivery, the project has no or only very small impact to students. | Some changes - The project delivery requires students to participate in some capacity or do some individual things differently. | Extensive - Students are strongly involved in the project or they need to do many things differently while the project is active (e.g. provide additional information or use alternate facilities). | Complex - There are several complex aspects which require deep engagement from students to get them right in the project.
Impact on staff (while delivering) | Minimum - During the delivery, the project has no or only very small impact to any staff. | Some - The project delivery requires staff in general (outside of the project team) to participate in some capacity or do some individual things differently. | Extensive - Staff are strongly involved in the project or they need to do many things differently while the project is active (e.g. use workarounds or alternate tools / facilities). | Complex - There are several complex aspects which require deep engagement from staff to get them right in the project.
Impact on external partners (while delivering) (other than the ones contracted to the project) | Minimum - During the delivery, the project has no or only very small impact to any external partners or vendors. | Some - The project delivery requires external partners or vendors to participate in some capacity or interact with ACU differently on individual things. | Extensive - External partners or vendors are strongly involved in the project or they need to do many things differently while the project is active (e.g. use workarounds or alternate communication channels). | Complex - The impact to our external partners is multi-faceted or high impact and requires very careful management. They need to do many things differently or are prevented from normal actions while the project is active.
Number of key stakeholders or groups impacted | 1 - One key stakeholder (group) is impacted directly during the project delivery. This would require them to do additional things or act differently while the project is active. | 2 - 3 - Two or three key stakeholders are impacted directly during the project delivery. This would require them to do additional things or act differently while the project is active. | 4 - 5 - Four or five key stakeholders are impacted directly during the project delivery. This would require them to do additional things or act differently while the project is active. | 6 or more - At least 6 different key stakeholders or groups are impacted directly during the project delivery. This would require them to do additional things or act differently while the project is active.
Changes to procedures, processes or work practices? | None - All work continues as before in the teams and units involved in or to be impacted by the project. | Some changes - Adjustments or small changes are required to accommodate the project work. | Extensive - Clear changes are required in the teams or units to accommodate the project work. This might involve relocations, using alternate equipment, or diffferent forms, reports, etc. | Complex - Complicated changes are required in the teams or units to accommodate the project work. This might involve changes in data access, tasks, roles & responsiblities, etc.
Overall complexity of the outputs | Simple - The outputs (deliverables) are easy to produce and the predictability is high. | Some changes - There is some complexity to the outputs and the project may encounter some challenges in creating them. | Extensive - The outputs in general are complex and creating them may require multiple parties. However, they are likely to be created and adopted into use successfully. | Complex - The outputs in general are complex and creating them may require multiple parties. Technical issues or other challenges are likely and they may be resource-intensive or difficult to resolve.
Level of innovation expected | None - The outputs are generally well known to ACU, using familiar components or functions. | Some - There are some elements new to ACU and they may prompt for new ways of working with those specific parts. | New to ACU - The solution delivered is new to ACU but used elsewhere in the sector. This introduces new work practices. | New to sector - The solution delivered is mostly new to the sector, at least in Australia. This introduces new work practices or approached to a University.
Interfacing expected with or impacts (dependencies) to other systems / products | None - We don't expect any interfaces to be needed or impacts to other systems. The proposed change works as stand-alone. | Simple - There will be interfaces or impacts to other systems but they are minor and simple to implement. | Few - There are few (2-4) integrations or dependenceis which require careful design. However, they usually rely on standardised methods and can be verified reliably. | Complex - There are multiple integration points or dependencies, or they are complex (e.g. tailored or purpose-built interfaces). The design and verification requires significant detailed work and expertise.
Future process collects, uses, stores or discloses personal information? | None - The data in the process or service contains no personal information. It may have been de-identified and no longer allows individuals to be identified. | Personal - The process or service will handle data which can be used to identify an individual. Examples: name, address, phone number, student or staff ID, photos. | Sensitive - The process or service will handle data which is sensitive in nature. Examples: sexual / religious / political orientation. Sensitive information has additional privacy requirements. | Health information – The process or service will handle data about an individual’s physical or mental health, symptoms, disability, genetics, bodily donations, future health wishes. It can also include health appointments, prescriptions, reports, job suitability based on health, healthcare identifiers. Health information is a subset of sensitive information but has extra limitations around use. | Sensitive information = information about racial or ethnic origin, political opinions, membership of a political association, religious beliefs or affiliations, philosophical beliefs, membership of a professional or trade association, membership of a trade union, sexual orientation or practices, or criminal record, or health information, genetic information or biometric information.
ACU familiarity with the potential product / system type? | Extensive - ACU uses or has used similar solutions in the past and has prior knowledge of the running and maintenance of these solutions. Advanced users are available for advice, if needed. | Comparable - ACU is familiar with comparable types of solutions and this experience can be applied on the solution implemented in this project. | Some - ACU is familiar with the types of solutions delivered by this project but lacks experience on this exact type or solution. It is likely that ACU needs training or other upskilling to become competent with this kinds of solutions. | None - This is likely to be a new kind of a solution so ACU requires user guidance and expertise, support capaiblity and other things to be developed from scratch.
How good fit or match to ACU are the solutions available to us? | 90% - Based on the current understanding, one or more solutions available to ACU are likely to be a very good fit. They offer the features ACU requires and appear to match the way ACU prefers to offer services. | 75% - One or more solutions provide a close match to ACU's expectations. However, it seems none of the solutions cater for all expectations and either they need enhancements or ACU's requirements need to be negotiated. | 50% - One or more solutions provide a partial match to ACU's expectations. However, it seems none of the solutions cater for all expectations and they may need several enhancements. ACU's requirements may need to be clearly altered. | 25% - The solutions available seem to provide some of the functionality expected but the gap with ACU's expectations is still big. This may necessitate the use of several systems or a purpose-built system to be developed.
Confidence that the right resources are available | Secured - The right resources have already been secured. This involves a direct control over their work or binding agreements with their management, agencies or vendors. | High - The right resources are likely to be available in full at the right time. This is supported either by at least partial control over their work or agreements with their management, agencies or vendors. | Medium - At least most of the required resources are likely to be available when needed. However, there is uncertainty whether all resources are available and the potential gaps are likely to impact the delivery. | Low - The availability of the right resources at the right time is uncertain. We may lack suitable resources or they may be reprioritised to other work despite of their project commitments.
Stability of requirements | Mandated - The requirements have been given to ACU and are based on a mandate (such as a regulation) which is likely to remain in place 'as is' through the project. | Stable - The requirements have been "locked in" and are unlikely to change. | Average - The requirements are scoped well but may still change somewhat. However, the purpose and outcome of the project is clear and project outputs have been agreed on. | Unstable - The requirements are likely to change, possibly significantly in parts. The outcome may also be adjusted.
Delivery schedules / deadlines | Free - The project can be delivered when possible and there are no specific timelines for it. | Flexible - The project can be started when possible but it is expected to be completed in one go without pauses. | Firm - The timeline is firm and only some changes can be negotiated. This would apply to e.g. functionality needed for the start of a semester. | Fixed - There is a specific timeline for this project, for its start, key milestones or completion. This may be set by a regulation or in an other non-negotiable manner.
Likely duration of the implementation (until project closure) | ≤ 6 mo - Based on the current understanding, this delivery is likely to be done in max 6 months. | 6 - 12 mo - Based on the current understanding, this delivery is likely to take more than 6 months but less than 12 months. | 1 - 2 years - Based on the current understanding, this delivery is likely to take at least 1 year but less than 2 years. | 2+ years - Based on the current understanding, this delivery is likely to be require at least 2 years. Note: Consider staging or splitting the project into shorter deliveries to lower the risk associated with long timelines.
Potential cost level of the impementation | ≤ $150 K - The project is likely to require max $150K of funding (capital and/or operating) for the delivery. | ≤ $250 K - The project is likely to require more than $150K but max $250K of funding. | ≤ $2 M - The project is likely to require more than $250K but max $2M of funding. These projects typically apply for capital funds. | $2+ M - The project is likely to require more than $2M of funding. These projects always apply for capital funds.

## Lookups
LOOKUPS USED IN THIS WORKBOOK
Please do not alter these without consultation with the Portfolio Projects Office (PPO)
|  | THRESHOLDS FOR CATEGORIES | Lower | Upper
|  | Complex | 15% | 49%
|  | Medium | 50% | 74%
|  | Simple | 75% | 100%
% CALCULATIONS AND WEIGHTS FOR THE RESULTS
|  | Contribution | Benefits $M | Benefits % | Cost $M | Capacity | Delivery % | ROI | Sum
| Weights: | 20% | 20% | 25% | 8% | 10% | 15% | 2% | 100% | Weighs can be adjusted but need prior consultation with PPO.
| Subtotals: | 20% | #REF! | 3.845% | #REF! | 1.667% | 2.25% | #REF! |  | Formulas are intended to remain as they are.
| Ratio: | 100% |  | 15.38% |  | 16.67% | 15% | #REF! |  | These values are used for the radar chart on the Results sheet.
LOOKUPS FOR MAGNITUDE
|  | Contractor cost | 900 | per resource per day |  |  | A typical daily fee. Can be adjusted but need prior consultation with PPO or Finance.
|  | Operational team cost | 649.3506 | per person per day |  |  | An average staff cost per workday. Can be adjusted but need prior consultation with PPO or Finance.
|  | Total resource cost (at 1 FTE) | 453600 |  |  |  | Formulas are intended to remain as they are.
|  | Multiplier | 8 | Based on process, system, uncertainties. |  |  | Formulas are intended to remain as they are.
|  | Cost estimate | 3628800
|  |  | PROJECT MAGNITUDE |  |  |  | Suggested magnitude based on the calculations.
|  |  | 1 | Operational
|  |  | 45000 | Simple
|  |  | 90000 | Simple or medium
|  |  | 225000 | Medium
|  |  | 450000 | Medium or complex
|  |  | 900000 | Complex
|  |  | LOOKUPS FOR SIZE OF BENEFITS |  |  |  | Suggested magnitude based on the calculations.
|  |  | Score | Value
|  |  | 1 | 1000001
|  |  | 2 | 250001
|  |  | 3 | 50001
|  |  | 4 | 1
LOOKUPS FOR EXPLANING THE OVERALL SCORE IN RESULTS
Selection | Contribution to priorities | Improvement to student experience | Improvement to staff experience | Improvement to operational efficiency | Broadness of impact
A | The change is not linked to any of ACU's expressed goals or priorities. | This change is not expected to alter the student experience. | This change is not expected to alter the staff experience. | This change is not expected to improve the current operational efficiency, or the improvement is ha | Students in a faculty / school or staff on campus, or staff at a unit level (org unit level 4 or be
B | Supporting - Implements a portfolio or local level priority, or enables other projects to implement priorities or strategic goals. | A refinement of an existing student experience or service. | A refinement of an existing staff experience or service. | Slight improvement in operations. Change 1 - 10% in time or cost of a service of function. | Single faculty / school or Directorate nationally (org unit level 3).
C | Strategic - Directly contributes to an ACU Strategic Plan 2023 goal or implements a VC Annual Priority focus area. | A distinct change or addition to an existing student experience or service. | A distinct change or addition to an existing staff experience or service. | Measurable adjustments in operations. Change 11 - 20% in time or cost of a service of function. | Students in multiple faculties or state-wide (e.g. MEL & BAL), or a portfolio nationally.
D | Mandatory for regulatory or WHS compliance reasons. Please reference the respective regulation or policy. | Developing new or redesigning experiences or services, transforming what is offered in an area. | Developing new or redesigning experiences or services, transforming what is offered in an area. | Significant improvement in operations through a changed process or system. The service capacity cha | All students or all staff nationally.
FINANCIAL BENEFITS AND EXPENSES IN THE PROPOSAL AND BUSINESS CASE
The impact of the resulting confidence ratings to the benefits and expenses is introduced below.
|  | Best case | Projected | Worst case
| Financial benefits | Benefits achieved in full without potential deductions. | Deduct 1/2 of the difference from 100%. | Deduct the difference from 100%.
| Project expenses | Optimistic estimate. | Optimistic estimate plus half of the difference between confidence % and 100%. | Optimistic estimate plus the difference between confidence % and 100%
| Example | Best case estimate | 80% of the estimate | 60% of the estimate
| Benefits: 60% | 500000 | 400000 | 300000
| Delivery: 80% | 1000000 | 1100000 | 1200000
|  | Best case estimate | Add (100% - 90%) = 10% to the estimate. | Add (100% - 80%) = 20% to the estimate.
If you have done a detailed assessment of risks and calculated the cost of your most significant risks and
deduction of benefits, you can use those figures to inform your Project Business Case.
|  | Best case | Projected | Worst case
| Financial benefits | Benefits in full without potential deductions. | Full benefits less deductions based on significant risks. | Full benefits less deductions from all risks.
| Project expenses | Optimistic estimate. | Optimistic estimate plus costs of significant risks. | Optimistic estimate plus costs of all risks.
Note on F12: Deducted from the total score.
Note on D19: $150,000 from Finance as an average salary cost of an ACU staff member, incl on-costs.

## BC delivery (hidden)
Product | Overall product / system | Simple | 2 | Average | 4 | Complex | 9
| Technology impact | Simple | 2 | Average | 5 | Complex | 9
| Organisational impact / HR processes | Simple | 1 | Average | 3 | Complex | 7
| Business process ownership | Embedded | 2 | Some | 5 | None | 9
| Data definition change / impact | Simple | 2 | Average | 5 | Complex | 9
| Interface to other systems / products | Simple | 2 | Average | 5 | Complex | 9
| New business / procedures alterations | None | 0 | Some | 3 | Extensive | 8
| Stability of requirements | Stable | 0 | Average | 5 | Unstable | 9
| Performance requirements incl. quality | Low | 1 | Average | 4 | High | 7
| Technology requirements | None | 0 | Some | 3 | Extensive | 8
| Complexity of target system environment | Low | 2 | Average | 5 | High | 9
| Level of technical innovation | None | 0 | Some | 6 | Innovative | 9
Team | Intrinsic team skills (general, interpersonal) | High | 1 | Average | 3 | Low | 6
| Relevant skill level with product / system type | Extensive | 1 | Some | 5 | None | 9
| Project manager experience | Extensive | 1 | Some | 5 | None | 9
| Use of contractors / part-timers | None | 0 | Some | 3 | Extensive | 6
| Project development length | < 6 months | 1 | 6 – 12 months | 3 | > 12 months | 8
| Project dependency upon external vendors | None | 0 | Some | 5 | Extensive | 9
| Degree of co-location of team | One room | 0 | One building | 5 | Virtual | 9
| Schedules / Deadlines | Flexible | 0 | Firm | 4 | Fixed | 8
| Priority for project team | High | 0 | Medium | 4 | Low | 8
| Team experience with product or hardware / software infrastructure | High | 1 | Medium | 5 | Low | 9
| Project team physical / support environment | Excellent | 0 | Average | 3 | Poor | 6
Environment/Stakeholders | Level of stakeholder support | High | 1 | Medium | 4 | Low | 9
| Stakeholder experience with project type | Extensive | 0 | Some | 3 | None | 6
| Sponsor support | High | 0 | Medium | 5 | Low | 9
| Impact on business operations (new technology, procedures, etc.) | None | 0 | Some | 5 | Extensive | 9
| Degree of change management required | None | 0 | Some | 3 | Extensive | 9
| Stakeholder participation | Full-time | 0 | Part-time | 3 | Ad-hoc | 6
| Critical dependence upon related projects | None | 0 | Some | 5 | Extensive | 9
| Number of business groups involved | 1 | 1 | 2019-03-01 | 4 | > 3 | 6
| Critical stakeholders | < 3 | 1 | 2019-10-03 | 5 | > 10 | 9

## BC benefits (hidden)
Benefits value chain | Overall outputs | Simple | 1 | Average | 3 | Complex | 9
| Outcome complexity | Simple | 2 | Average | 5 | Complex | 9
| Size of total financial benefits | > $5Mill | 1 | $1 - $5Mill | 3 | < $1Mill | 6
| Expected pay-back period | < 1 Year | 1 | 2 Years | 5 | > 2 Years | 9
| Impact of non-financial benefits | None | 0 | Some | 3 | Extensive | 6
| Time for outputs to become outcomes | < 3 Months | 1 | 4 Months –1 Yr | 6 | > 1 Year | 9
| Output / Outcomes impact on stakeholders / customers | Positive | 0 | Neutral | 3 | Negative | 9
| Complexity of benefit realisation chain | Direct to outcome | 1 | Outcome to impact | 5 | Beyond impact | 9
| Complexity of support processes | Simple | 1 | Average | 3 | Complex | 6
Benefits realisation process | Complexity of business process change required | Low | 1 | Average | 3 | High | 9
| Degree of cultural, business process change required | None | 0 | Some | 5 | Extensive | 9
| Organisational openness to change | Open | 0 | Some | 4 | Resistant | 9
| Number of PU leaders / benefit owners involved | 1 | 0 | 2 – 10 | 3 | > 10 | 7
| Number of external stakeholders groups involved | 0 | 0 | 1 | 3 | > 1 | 7
| Percentage of organisation impacted by realisation process | < 10% | 2 | 10 – 25% | 5 | > 25% | 9
Benefits realisation governance | Sponsor experience in similar projects | Extensive | 1 | Some | 3 | None | 6
| Impact on sponsor (career, KPI, etc.) | High | 1 | Medium | 3 | Low | 6
| Impact on NAB operations (new technology, procedures, etc.) from lack of realisation | None | 1 | Some | 3 | Extensive | 9
| Expectation of sponsor remaining throughout realisation | Certain | 1 | Likely | 5 | Low | 7